## Today RT list of defects
# | Customer | Subject | Status | QueueName | OwnerName | Priority | Defect # | Requestors | Created | Told | LastUpdated | Due | CustomField.{Current Status} | CustomField.{Ticket Severity} | CAC/MOF Requestor | Ministry/FFX Owner | CAC/MOF/FFX Owner
104174 |  | SEV 3 - Batches in Error with No Message | open | Projects - Ontario - PROD | andy.herdlein (Andy Herdlein) | 9 |  | ben.whyte (Ben Whyte) | Mon, Apr 22, 2024 10:45:00 AM | Tue, May 7, 2024 11:40:29 AM | Tue, May 7, 2024 6:27:25 PM | Not set | Researching | Severity 3 | CAC | FFX | FFX
104203 |  | Payment Source Report | resolved | Projects - Ontario - PROD | brenda.boyle (Brenda Boyle) | 10 |  | brenda.boyle (Brenda Boyle) | Tue, Apr 23, 2024 11:29:34 AM | Tue, Apr 23, 2024 11:51:19 AM | Tue, May 21, 2024 1:26:35 PM | Not set | Customer Testing | Severity 2 | MOF | Ministry | MOF
104204 |  | Payment Source Report Updates | open | Projects - Ontario - PROD | brian.smedley (Brian Smedley) | 9 |  | donna.schmitz (Donna Schmitz) | Tue, Apr 23, 2024 1:16:22 PM | Not set | Tue, May 21, 2024 8:09:08 AM | Not set | Assigned to Projects | Severity 2 | FFX | FFX | FFX
104253 | 20240424032477000 | IFIS S2 Voucher - Edit No Money | open | Projects - Ontario - PROD | andy.herdlein (Andy Herdlein) | 10 |  | brenda.boyle (Brenda Boyle) | Thu, Apr 25, 2024 10:03:47 AM | Fri, May 17, 2024 10:26:41 AM | Mon, May 20, 2024 5:12:38 PM | Not set | Assigned to Projects | Severity 4 | MOF | FFX | FFX
104341 | 20240429027490 | SEV 3 - IFTA Schedule Non-Standard - Missing Math Blocks and Val Rules - Rows 19-100 | resolved | Projects - Ontario - PROD | catherine.ryan (Catherine Ryan) | 11 |  | catherine.ryan (Catherine Ryan) | Tue, Apr 30, 2024 10:06:19 AM | Fri, May 3, 2024 12:03:46 PM | Fri, May 17, 2024 11:52:44 AM | Not set | Customer Testing | Severity 3 | CAC | Ministry | CAC
104342 |  | CR73 - Daily Bank Deposit Summary Report | stalled | Projects - Ontario - PROD | jeff.jostes (Jeff Jostes) | 4 |  | brenda.boyle (Brenda Boyle) | Tue, Apr 30, 2024 10:06:48 AM | Not set | Tue, May 21, 2024 8:33:25 AM | Not set | Create CR/SOW | Severity 2 | MOF | FFX | FFX
104379 | Cheque Negotiability Validation Rules - Updates Needed | Update Validation Rules - Cheque Negotiability | stalled | Projects - Ontario - PROD | tamara.gardner (Tamara Gardner) | 0 |  | tamara.gardner (Tamara Gardner) | Wed, May 1, 2024 9:42:41 AM | Not set | Thu, May 16, 2024 10:48:23 AM | Not set | Create CR/SOW | Severity 2 | MOF | Ministry | MOF
104421 |  | SEV 3 - Foreign Exchange Notification Email not ingested by FFX | resolved | Projects - Ontario - PROD | ben.whyte (Ben Whyte) | 8 |  | ben.whyte (Ben Whyte) | Thu, May 2, 2024 2:27:24 PM | Tue, May 21, 2024 11:40:19 AM | Tue, May 21, 2024 11:40:19 AM | Not set | Customer Testing | Severity 3 | CAC | Ministry | CAC
104425 |  | SEV 3 - OPEX scanners accepting double feed without alerts | started | Projects - Ontario - PROD | jeff.jostes (Jeff Jostes) | 0 |  | ben.whyte (Ben Whyte) | Thu, May 2, 2024 4:15:21 PM | Not set | Thu, May 9, 2024 2:02:41 PM | Not set | Meeting To Be Scheduled | Severity 3 | CAC | FFX | FFX
104470 |  | IMAGE Only - correspondence | open | Projects - Ontario - PROD | fredrick.little (Fredrick Little) | 9 |  | brenda.boyle (Brenda Boyle) | Tue, May 7, 2024 10:13:27 AM | Wed, May 8, 2024 6:57:39 AM | Mon, May 20, 2024 11:25:13 AM | Not set | Assigned to Projects | Severity 2 | MOF | FFX | FFX
104471 |  | Sev 2 - Exchange Rate | stalled | Projects - Ontario - PROD | brenda.boyle (Brenda Boyle) | 9 |  | cynthia.ogbeide (Cynthia Ogbeide) | Tue, May 7, 2024 10:15:13 AM | Wed, May 8, 2024 10:08:24 AM | Thu, May 16, 2024 10:48:23 AM | Not set | Create CR/SOW | Severity 2 | MOF | Ministry | MOF
104509 | 20240501016961 | Severity 4 MIT_SCHED_6_L The hotboxes of Total Max exemption Per Mine and Lesser Amount B issue | open | Projects - Ontario - PROD | ben.whyte (Ben Whyte) | 0 |  | jingxin.jiang (Jingxin Jiang) | Wed, May 8, 2024 4:24:03 PM | Not set | Thu, May 9, 2024 8:07:31 AM | Not set | Waiting on Customer | Severity 4 | CAC | Ministry | CAC
104511 |  | Severity 4 AC Base Amount less Total(120) on MIT_SCHED_6_L does not has input field in the interface | open | Projects - Ontario - PROD | ben.whyte (Ben Whyte) | 0 |  | jingxin.jiang (Jingxin Jiang) | Wed, May 8, 2024 4:31:49 PM | Not set | Thu, May 9, 2024 8:07:57 AM | Not set | Waiting on Customer | Severity 4 | CAC | Ministry | CAC
104523 |  | SEV 2 - Prevent $0.00 payment vouchers from advancing through Balance Queue | stalled | Projects - Ontario - PROD | ben.whyte (Ben Whyte) | 0 |  | ben.whyte (Ben Whyte) | Thu, May 9, 2024 10:54:17 AM | Not set | Thu, May 16, 2024 10:48:23 AM | Not set | Create CR/SOW | Severity 2 | CAC | Ministry | CAC
104539 |  | SEV 3 - MIT Virtual Voucher Validation Rule Change on Account ID | stalled | Projects - Ontario - PROD | jeff.jostes (Jeff Jostes) | 0 |  | ben.whyte (Ben Whyte) | Thu, May 9, 2024 3:05:42 PM | Mon, May 13, 2024 9:12:54 AM | Thu, May 16, 2024 10:48:23 AM | Not set | Create CR/SOW | Severity 3 | CAC | FFX | FFX
104589 |  | Modify Cheque Date missing from Quick Key for Level 4 Access | resolved | Projects - Ontario - PROD | ben.whyte (Ben Whyte) | 9 |  | brenda.boyle (Brenda Boyle) | Mon, May 13, 2024 9:29:53 AM | Fri, May 17, 2024 12:10:27 PM | Mon, May 20, 2024 4:40:50 PM | Not set | Customer Testing | Severity 3 | MOF | Ministry | CAC
104603 | 20240507041137008 | CARLAR resets moving between Quick Review and Quick Key | resolved | Projects - Ontario - PROD | brenda.boyle (Brenda Boyle) | 7 |  | brenda.boyle (Brenda Boyle) | Mon, May 13, 2024 3:53:44 PM | Thu, May 16, 2024 2:27:18 PM | Fri, May 17, 2024 12:04:04 PM | Not set | Customer Testing | Severity 2 | MOF | Ministry | MOF
104621 |  | SEV 3 - Ensure any negative values in Rows 19-100 of IFT_QUAR_SCHED_NON output to F023 properly | resolved | Projects - Ontario - PROD | ben.whyte (Ben Whyte) | 9 |  | ben.whyte (Ben Whyte) | Tue, May 14, 2024 8:35:06 AM | Fri, May 17, 2024 11:19:41 AM | Fri, May 17, 2024 11:19:41 AM | Not set | Customer Testing | Severity 3 | CAC | Ministry | CAC
104642 |  | New Report - Field Recognition Accuracy Detail Report by Batch Type | stalled | Projects - Ontario - PROD | jeff.jostes (Jeff Jostes) | 0 |  | tamara.gardner (Tamara Gardner) | Tue, May 14, 2024 11:31:52 AM | Not set | Thu, May 16, 2024 10:48:23 AM | Not set | Create CR/SOW | Severity 2 | MOF | FFX | FFX
104684 |  | EditMoney Error - Correspondence_Rear with Separators | open | Projects - Ontario - PROD | brenda.boyle (Brenda Boyle) | 9 |  | brenda.boyle (Brenda Boyle) | Thu, May 16, 2024 8:10:15 AM | Not set | Thu, May 16, 2024 3:57:22 PM | Not set | Waiting on Customer | Severity 3 | MOF | Ministry | MOF
104695 |  | F010: Modify Journal Name in DCR and Detail Records For Direct Deposits | resolved | Projects - Ontario - PROD | aravinth.ramalingam (Aravinth Ramalingam) | 9 |  | aravinth.ramalingam (Aravinth Ramalingam) | Thu, May 16, 2024 12:08:37 PM | Fri, May 17, 2024 12:28:16 PM | Tue, May 21, 2024 8:08:19 AM | Not set | Customer Testing | Severity 2 | CAC | Ministry | CAC
104696 |  | F060: Modify Journal Name in DCR and Detail Records For Direct Deposits | resolved | Projects - Ontario - PROD | aravinth.ramalingam (Aravinth Ramalingam) | 9 |  | aravinth.ramalingam (Aravinth Ramalingam) | Thu, May 16, 2024 12:12:45 PM | Not set | Tue, May 21, 2024 8:08:09 AM | Not set | Customer Testing | Severity 2 | CAC | Ministry | CAC
104728 |  | SEV 2 - Unbalanced DD_NOTIF and Virtual S2 voucher went to output | resolved | Projects - Ontario - PROD | jeff.jostes (Jeff Jostes) | 10 |  | ben.whyte (Ben Whyte) | Fri, May 17, 2024 10:53:37 AM | Not set | Tue, May 21, 2024 7:51:08 AM | Not set | Pending Release | Severity 2 | CAC | FFX | FFX
104732 | 20240515017077 20240515017078 | Sev 4: IFT_QUAR_SCHED_NON_L 2 Minor Issues | resolved | Projects - Ontario - PROD | jeff.jostes (Jeff Jostes) | 9 |  | catherine.ryan (Catherine Ryan) | Fri, May 17, 2024 11:35:21 AM | Not set | Mon, May 20, 2024 3:04:28 PM | Not set | Pending Release | Severity 4 | CAC | FFX | FFX
104748 |  | SEV 2 - Virtual S2 vouchers going to output without being keyed | resolved | Projects - Ontario - PROD | jeff.jostes (Jeff Jostes) | 10 |  | ben.whyte (Ben Whyte) | Fri, May 17, 2024 2:55:45 PM | Not set | Mon, May 20, 2024 5:36:52 PM | Not set | Pending Release | Severity 2 | CAC | FFX | FFX

## Pivot Table
Count of CAC/MOF Requestor | Column Labels
Row Labels | Assigned to Projects | Create CR/SOW | Customer Testing | Researching | Waiting on Customer | FFX Testing | Meeting To Be Scheduled | Grand Total
CAC | 2 | 2 | 2 | 1 | 2 | 1 | 1 | 11
MOF | 4 | 3 | 2 |  | 1 |  |  | 10
FFX | 1 | [6 empty] | 1
Grand Total | 7 | 5 | 4 | 1 | 3 | 1 | 1 | 22
Count of Status | Column Labels
Row Labels | Severity 2 | Severity 3 | Severity 4 | Grand Total
resolved | 2 | 2 |  | 4
stalled | 5 | 1 |  | 6
ffxqa |  | 1 |  | 1
open | 3 | 3 | 4 | 10
started |  | 1 |  | 1
Grand Total | 10 | 8 | 4 | 22
Count of Status | Column Labels
Row Labels | Assigned to Projects | Create CR/SOW | Customer Testing | Researching | Waiting on Customer | FFX Testing | Meeting To Be Scheduled | Grand Total
resolved |  |  | 4 |  |  |  |  | 4
stalled | 1 | 5 | [5 empty] | 6
ffxqa | [5 empty] | 1 |  | 1
open | 6 |  |  | 1 | 3 |  |  | 10
started | [6 empty] | 1 | 1
Grand Total | 7 | 5 | 4 | 1 | 3 | 1 | 1 | 22
Count of Status | Column Labels
Row Labels | Severity 2 | Severity 3 | Severity 4 | Grand Total
CAC | 1 | 2 | 3 | 6
FFX | 5 | 5 | 1 | 11
MOF | 4 | 1 |  | 5
Grand Total | 10 | 8 | 4 | 22
Count of Status | Column Labels
Row Labels | CAC | MOF | FFX | Grand Total
Severity 2 | 2 | 7 | 1 | 10
Severity 3 | 6 | 2 |  | 8
Severity 4 | 3 | 1 |  | 4
Grand Total | 11 | 10 | 1 | 22
Count of Ministry/FFX Owner | CustomField.{Ticket Severity}
Ministry/FFX Owner | Severity 2 | Severity 3 | Severity 4 | Grand Total
FFX | 5 | 5 | 1 | 11
Ministry | 5 | 3 | 3 | 11
Grand Total | 10 | 8 | 4 | 22
Count of CAC/MOF/FFX Owner | CustomField.{Ticket Severity}
CAC/MOF/FFX Owner | Severity 2 | Severity 3 | Severity 4 | Grand Total
MOF | 4 | 1 |  | 5
CAC | 1 | 2 | 3 | 6
FFX | 5 | 5 | 1 | 11
Grand Total | 10 | 8 | 4 | 22
Count of Status | Column Labels
Row Labels | Severity 2 | Severity 3 | Severity 4 | Grand Total
resolved | 2 | 2 |  | 4
stalled | 5 | 1 |  | 6
ffxqa |  | 1 |  | 1
open | 3 | 3 | 4 | 10
started |  | 1 |  | 1
Grand Total | 10 | 8 | 4 | 22

## Graphs
Do not delete sheet
Defects | Number
New Defects Today | 2
Defects Closed Today | 14
Total | 16
CAC/MOF Requestor | Assigned to Projects | Create CR/SOW | Customer Testing | Researching | Waiting on Customer | FFX Testing | Meeting To Be Scheduled | Grand Total
CAC | 2 | 2 | 2 | 1 | 2 | 1 | 1 | 11
MOF | 4 | 3 | 2 | 0 | 1 | 0 | 0 | 10
FFX | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Grand Total | 7 | 5 | 4 | 1 | 3 | 1 | 1 | 22
Status | Severity 2 | Severity 3 | Severity 4 | Grand Total
resolved | 2 | 2 | 0 | 4
stalled | 5 | 1 | 0 | 6
ffxqa | 0 | 1 | 0 | 1
open | 3 | 3 | 4 | 10
started | 0 | 1 | 0 | 1
Grand Total | 10 | 8 | 4 | 22
Row Labels | Assigned to Projects | Create CR/SOW | Customer Testing | Researching | Waiting on Customer | FFX Testing | Meeting To Be Scheduled | Grand Total
resolved | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4
stalled | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 6
ffxqa | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1
open | 6 | 0 | 0 | 1 | 3 | 0 | 0 | 10
started | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Grand Total | 7 | 5 | 4 | 1 | 3 | 1 | 1 | 22
CAC/MOF/FFX Owner | Severity 2 | Severity 3 | Severity 4 | Grand Total
CAC | 1 | 2 | 3 | 6
FFX | 5 | 5 | 1 | 11
MOF | 4 | 1 | 0 | 5
Grand Total | 10 | 8 | 4 | 22
Severity by Requestor | CAC | MOF | FFX | Total
Severity 2 tickets | 2 | 7 | 1 | 10
Severity 3 tickets | 6 | 2 | 0 | 8
Severity 4 tickets | 3 | 1 | 0 | 4
Blank (No Severity) | 0 | 0 | 0 | 0
Total | 11 | 10 | 1 | 22
Ticket Owner | Number of Tickets
FFX | 11
Ministry | 11
Total | 22
Ticket Owner | # Sev 2 Tickets
MOF | 4
CAC | 1
FFX | 5
Grand Total | 10
Ticket Owner | Total # Tickets
MOF | 5
CAC | 6
FFX | 11
Grand Total | 22

## Requestors & Owners
Owner | MOF/CAC | Requestors | CAC/MOF | Do not delete sheet, hide if needed
nicholas.landry (Nicholas Landry) | CAC | ben.whyte (Ben Whyte) | CAC | Do not move columns in this sheet, if needed edit or add data only in same columns
ben.whyte (Ben Whyte) | CAC | Lisa.Leger <Lisa.Leger@ontario.ca> | CAC
lisa.parsons (Lisa Parsons) | CAC | nicholas.landry (Nicholas Landry) | CAC
jingxin.jiang | CAC | aravinth.ramalingam (Aravinth Ramalingam) | CAC
colleen.pacione (Colleen Pacione) | CAC | lisa.parsons (Lisa Parsons) | CAC
catherine.ryan (Catherine Ryan) | CAC | jingxin.jiang (Jingxin Jiang) | CAC
mariaalejandra.gonzalezmoctezuma (Maria Alejandra Gonzalez Moctezuma) | CAC | colleen.pacione (Colleen Pacione) | CAC
aravinth.ramalingam (Aravinth Ramalingam) | CAC | catherine.ryan (Catherine Ryan) | CAC
bukola.ogeleka (Bukola Ogeleka) | MOF | mariaalejandra.gonzalezmoctezuma (Maria Alejandra Gonzalez Moctezuma) | CAC
tejumade.adenle | MOF | cynthia.ogbeide (Cynthia Ogbeide) | MOF
cynthia.ogbeide (Cynthia Ogbeide) | MOF | Tejumade.Adenle@ontario.ca | MOF
tamara.gardner (Tamara Gardner) | MOF | brenda.boyle (Brenda Boyle) | MOF
sabrina.difrancesco | MOF | bukola.ogeleka (Bukola Ogeleka) | MOF
jeff.jostes (Jeff Jostes) | FFX | tamara.gardner (Tamara Gardner) | MOF
mason.graham | FFX | Sabrina.DiFrancesco@ontario.ca | MOF
amit.dudhat | FFX | shahadat.hossain (Shahadat Hossain) | CAC
francesco.leising (Francesco Leising) | FFX | romnick.galang (Romnick Galang) | CAC
fredrick.little (Fredrick Little) | FFX | allana.allen (Allana Allen) | MOF
andy.herdlein (Andy Herdlein) | FFX | Azhar.Ahmad@ontario.ca | CAC
joe.gero | FFX | farzana.aziz (Farzana Aziz ) | MOF
alyssa.dinoto | FFX | donna.schmitz (Donna Schmitz) | FFX
brian.smedley (Brian Smedley) | FFX | jeff.jostes (Jeff Jostes) | FFX
alex.umansky | FFX | mohammad.shamsi (Mohammad Shamsi) | CAC
molly.vanryn | FFX
phil.cannon | FFX
shahadat.hossain | CAC
ehizogie.ighile | FFX
allana.allen (Allana Allen) | MOF
romnick.galang | CAC
paul.scott (Paul A Scott) | MOF
leann.stout | FFX
chris.bosner | FFX
brenda.boyle (Brenda Boyle) | MOF
donna.schmitz (Donna Castello) | FFX
tyler.cabell | FFX
joe.gero (Joe Gero) | FFX
donna.schmitz (Donna Schmitz) | FFX
kevin.powell (Kevin Powell) | CAC
farzana.aziz (Farzana Aziz ) | MOF
mohammad.shamsi (Mohammad Shamsi) | CAC