## Sheet1
# | Customer | Subject | Status | QueueName | OwnerName | Priority | Defect # | Requestors | Created | Told | LastUpdated | Due | CustomField.{Current Status} | CustomField.{Ticket Severity}
104204 |  | Payment Source Report Updates | resolved | Projects - Ontario - PROD | farzana.aziz (Farzana Aziz ) | 10 |  | donna.schmitz (Donna Schmitz) | Tue, Apr 23, 2024 1:16:22 PM | Not set | Thu, May 30, 2024 1:47:33 PM | Not set | Customer Testing | Severity 2
104342 |  | CR75 - Daily Bank Deposit Summary Report | stalled | Projects - Ontario - PROD | jeff.jostes (Jeff Jostes) | 4 |  | brenda.boyle (Brenda Boyle) | Tue, Apr 30, 2024 10:06:48 AM | Not set | Thu, May 23, 2024 9:47:51 AM | Not set | Create CR/SOW | Severity 2
104379 | Cheque Negotiability Validation Rules - Updates Needed | Update Validation Rules - Cheque Negotiability | stalled | Projects - Ontario - PROD | tamara.gardner (Tamara Gardner) | 0 |  | tamara.gardner (Tamara Gardner) | Wed, May 1, 2024 9:42:41 AM | Not set | Thu, May 16, 2024 10:48:23 AM | Not set | Create CR/SOW | Severity 2
104425 |  | SEV 3 - OPEX scanners accepting double feed without alerts | started | Projects - Ontario - PROD | jeff.jostes (Jeff Jostes) | 0 |  | ben.whyte (Ben Whyte) | Thu, May 2, 2024 4:15:21 PM | Not set | Thu, May 9, 2024 2:02:41 PM | Not set | Meeting To Be Scheduled | Severity 3
104523 |  | SEV 2 - Prevent $0.00 payment vouchers from advancing through Balance Queue | stalled | Projects - Ontario - PROD | ben.whyte (Ben Whyte) | 0 |  | ben.whyte (Ben Whyte) | Thu, May 9, 2024 10:54:17 AM | Not set | Thu, May 16, 2024 10:48:23 AM | Not set | Create CR/SOW | Severity 2
104539 |  | SEV 3 - MIT Virtual Voucher Validation Rule Change on Account ID | stalled | Projects - Ontario - PROD | jeff.jostes (Jeff Jostes) | 0 |  | ben.whyte (Ben Whyte) | Thu, May 9, 2024 3:05:42 PM | Mon, May 13, 2024 9:12:54 AM | Thu, May 16, 2024 10:48:23 AM | Not set | Create CR/SOW | Severity 3
104642 |  | New Report - Field Recognition Accuracy Detail Report by Batch Type | stalled | Projects - Ontario - PROD | jeff.jostes (Jeff Jostes) | 0 |  | tamara.gardner (Tamara Gardner) | Tue, May 14, 2024 11:31:52 AM | Not set | Thu, May 16, 2024 10:48:23 AM | Not set | Create CR/SOW | Severity 2
104684 |  | EditMoney Error - Correspondence_Rear with Separators | resolved | Projects - Ontario - PROD | brenda.boyle (Brenda Boyle) | 9 |  | brenda.boyle (Brenda Boyle) | Thu, May 16, 2024 8:10:15 AM | Not set | Tue, May 28, 2024 7:55:28 PM | Not set | Customer Testing | Severity 3
104836 | 20240521940001000 | Sev 4 - Emails being split into multiple documents in EPIC | stalled | Projects - Ontario - PROD | lisa.parsons (Lisa Parsons) | 0 |  | lisa.parsons (Lisa Parsons) | Thu, May 23, 2024 9:25:52 AM | Not set | Thu, May 23, 2024 2:04:26 PM | Not set | Create CR/SOW | Severity 4
104843 |  | MIT Virtual Voucher- Installment payment type | stalled | Projects - Ontario - PROD | tamara.gardner (Tamara Gardner) | 0 |  | brenda.boyle (Brenda Boyle) | Thu, May 23, 2024 1:29:09 PM | Thu, May 23, 2024 2:39:21 PM | Thu, May 23, 2024 2:39:21 PM | Not set | Create CR/SOW | Severity 3
104852 |  | Illegible DLN Burn on FTP supporting documents | stalled | Projects - Ontario - PROD | brenda.boyle (Brenda Boyle) | 0 |  | brenda.boyle (Brenda Boyle) | Fri, May 24, 2024 8:44:30 AM | Not set | Wed, May 29, 2024 5:53:51 AM | Not set | Create CR/SOW | Severity 4
104899 |  | SEV 2 - Transactions with multiple Post-Date Cheques sent back to start of Boundary 2, not going through CustomSplit | resolved | Projects - Ontario - PROD | ben.whyte (Ben Whyte) | 0 |  | ben.whyte (Ben Whyte) | Tue, May 28, 2024 10:40:16 AM | Tue, May 28, 2024 11:48:28 AM | Tue, May 28, 2024 7:55:02 PM | Not set | Customer Testing | Severity 2
104963 |  | System not requesting operator key for Postmark date in CheckOnly queue when processing IFTA voucher | open | Projects - Ontario - PROD | andy.herdlein (Andy Herdlein) | 9 |  | ayesa.parvin (Ayesa Parvin) | Thu, May 30, 2024 10:16:34 AM | Not set | Thu, May 30, 2024 10:28:02 AM | Not set | Customer Generated Ticket | Severity 4