## Today RT list of defects
# | Customer | Subject | Status | OwnerName | Requestors | Created | Told | LastUpdated | Due | CustomField.{Current Status} | CustomField.{Ticket Severity} | CAC/MOF Requestor | Ministry/FFX Owner | CAC/MOF/FFX Owner
104204 |  | Payment Source Report Updates | resolved | farzana.aziz (Farzana Aziz ) | donna.schmitz (Donna Schmitz) | Tue, Apr 23, 2024 1:16:22 PM | Not set | Thu, May 30, 2024 4:59:26 PM | Not set | Customer Testing | Severity 2 | FFX | Ministry | MOF
104342 |  | CR75 - Daily Bank Deposit Summary Report | stalled | jeff.jostes (Jeff Jostes) | brenda.boyle (Brenda Boyle) | Tue, Apr 30, 2024 10:06:48 AM | Not set | Thu, May 23, 2024 9:47:51 AM | Not set | Create CR/SOW | Severity 2 | MOF | FFX | FFX
104379 | Cheque Negotiability Validation Rules - Updates Needed | Update Validation Rules - Cheque Negotiability | stalled | tamara.gardner (Tamara Gardner) | tamara.gardner (Tamara Gardner) | Wed, May 1, 2024 9:42:41 AM | Not set | Thu, May 16, 2024 10:48:23 AM | Not set | Create CR/SOW | Severity 2 | MOF | Ministry | MOF
104425 |  | SEV 3 - OPEX scanners accepting double feed without alerts | started | jeff.jostes (Jeff Jostes) | ben.whyte (Ben Whyte) | Thu, May 2, 2024 4:15:21 PM | Not set | Thu, May 9, 2024 2:02:41 PM | Not set | Meeting To Be Scheduled | Severity 3 | CAC | FFX | FFX
104523 |  | SEV 2 - Prevent $0.00 payment vouchers from advancing through Balance Queue | stalled | ben.whyte (Ben Whyte) | ben.whyte (Ben Whyte) | Thu, May 9, 2024 10:54:17 AM | Not set | Thu, May 16, 2024 10:48:23 AM | Not set | Create CR/SOW | Severity 2 | CAC | Ministry | CAC
104539 |  | SEV 3 - MIT Virtual Voucher Validation Rule Change on Account ID | stalled | jeff.jostes (Jeff Jostes) | ben.whyte (Ben Whyte) | Thu, May 9, 2024 3:05:42 PM | Mon, May 13, 2024 9:12:54 AM | Thu, May 16, 2024 10:48:23 AM | Not set | Create CR/SOW | Severity 3 | CAC | FFX | FFX
104642 |  | New Report - Field Recognition Accuracy Detail Report by Batch Type | stalled | jeff.jostes (Jeff Jostes) | tamara.gardner (Tamara Gardner) | Tue, May 14, 2024 11:31:52 AM | Not set | Thu, May 16, 2024 10:48:23 AM | Not set | Create CR/SOW | Severity 2 | MOF | FFX | FFX
104684 |  | EditMoney Error - Correspondence_Rear with Separators | resolved | brenda.boyle (Brenda Boyle) | brenda.boyle (Brenda Boyle) | Thu, May 16, 2024 8:10:15 AM | Not set | Tue, May 28, 2024 7:55:28 PM | Not set | Customer Testing | Severity 3 | MOF | Ministry | MOF
104836 | 20240521940001000 | Sev 4 - Emails being split into multiple documents in EPIC | stalled | lisa.parsons (Lisa Parsons) | lisa.parsons (Lisa Parsons) | Thu, May 23, 2024 9:25:52 AM | Not set | Thu, May 23, 2024 2:04:26 PM | Not set | Create CR/SOW | Severity 4 | CAC | Ministry | CAC
104843 |  | MIT Virtual Voucher- Installment payment type | stalled | tamara.gardner (Tamara Gardner) | brenda.boyle (Brenda Boyle) | Thu, May 23, 2024 1:29:09 PM | Thu, May 23, 2024 2:39:21 PM | Thu, May 23, 2024 2:39:21 PM | Not set | Create CR/SOW | Severity 3 | MOF | Ministry | MOF
104852 |  | Illegible DLN Burn on FTP supporting documents | stalled | brenda.boyle (Brenda Boyle) | brenda.boyle (Brenda Boyle) | Fri, May 24, 2024 8:44:30 AM | Not set | Wed, May 29, 2024 5:53:51 AM | Not set | Create CR/SOW | Severity 4 | MOF | Ministry | MOF
104899 |  | SEV 2 - Transactions with multiple Post-Date Cheques sent back to start of Boundary 2, not going through CustomSplit | open | ben.whyte (Ben Whyte) | ben.whyte (Ben Whyte) | Tue, May 28, 2024 10:40:16 AM | Tue, May 28, 2024 11:48:28 AM | Fri, May 31, 2024 3:44:28 PM | Not set | Customer Testing | Severity 2 | CAC | Ministry | CAC
104963 |  | System not requesting operator key for Postmark date in CheckOnly queue when processing IFTA voucher | resolved | jeff.jostes (Jeff Jostes) | ayesa.parvin (Ayesa Parvin) | Thu, May 30, 2024 10:16:34 AM | Not set | Mon, Jun 3, 2024 9:53:23 AM | Not set | Pending Release | Severity 4 | CAC | FFX | FFX
104987 |  | CustomSplit queue not visible from Workflow Monitor | resolved | lisa.parsons (Lisa Parsons) | lisa.parsons (Lisa Parsons) | Fri, May 31, 2024 8:33:05 AM | Not set | Sun, Jun 2, 2024 11:16:28 AM | Not set | Customer Testing | Severity 3 | CAC | Ministry | CAC
105012 | 20240429500014000 | Severity 2 IFIS voucher shouldn't show up in PostAction | resolved | jeff.jostes (Jeff Jostes) | jingxin.jiang (Jingxin Jiang) | Fri, May 31, 2024 12:40:17 PM | Not set | Mon, Jun 3, 2024 2:38:58 PM | Not set | Pending Release | Severity 2 | CAC | FFX | FFX

## Pivot Table
Count of CAC/MOF Requestor | Column Labels
Row Labels | Create CR/SOW | Customer Testing | Meeting To Be Scheduled | Pending Release | Grand Total
CAC | 3 | 2 | 1 | 2 | 8
FFX | 0 | 1 | 0 | 0 | 1
MOF | 5 | 1 | 0 | 0 | 6
Grand Total | 8 | 4 | 1 | 2 | 15
Count of Status | Column Labels
Row Labels | Severity 2 | Severity 3 | Severity 4 | Grand Total
open | 1 | 0 | 0 | 1
resolved | 2 | 2 | 1 | 5
stalled | 4 | 2 | 2 | 8
started | 0 | 1 | 0 | 1
Grand Total | 7 | 5 | 3 | 15
Count of Status | Column Labels
Row Labels | Create CR/SOW | Customer Testing | Meeting To Be Scheduled | Pending Release | Grand Total
open | 0 | 1 | 0 | 0 | 1
resolved | 0 | 3 | 0 | 2 | 5
stalled | 8 | 0 | 0 | 0 | 8
started | 0 | 0 | 1 | 0 | 1
Grand Total | 8 | 4 | 1 | 2 | 15
Count of Status | Column Labels
Row Labels | Severity 2 | Severity 3 | Severity 4 | Grand Total
CAC | 2 | 1 | 1 | 4
FFX | 3 | 2 | 1 | 6
MOF | 2 | 2 | 1 | 5
Grand Total | 7 | 5 | 3 | 15
Count of Status | Column Labels
Row Labels | CAC | FFX | MOF | Grand Total
Severity 2 | 3 | 1 | 3 | 7
Severity 3 | 3 | 0 | 2 | 5
Severity 4 | 2 | 0 | 1 | 3
Grand Total | 8 | 1 | 6 | 15
Count of Ministry/FFX Owner | CustomField.{Ticket Severity}
Ministry/FFX Owner | Severity 2 | Severity 3 | Severity 4 | Grand Total
FFX | 3 | 2 | 1 | 6
Ministry | 4 | 3 | 2 | 9
Grand Total | 7 | 5 | 3 | 15
Count of CAC/MOF/FFX Owner | CustomField.{Ticket Severity}
CAC/MOF/FFX Owner | Severity 2 | Severity 3 | Severity 4 | Grand Total
CAC | 2 | 1 | 1 | 4
FFX | 3 | 2 | 1 | 6
MOF | 2 | 2 | 1 | 5
Grand Total | 7 | 5 | 3 | 15
Count of Status | Column Labels
Row Labels | Severity 2 | Severity 3 | Severity 4 | Grand Total
open | 1 | 0 | 0 | 1
resolved | 2 | 2 | 1 | 5
stalled | 4 | 2 | 2 | 8
started | 0 | 1 | 0 | 1
Grand Total | 7 | 5 | 3 | 15

## Graphs
Defects | Number
New Defects Today | 0
Defects Closed Today | 0
Total | 0
CAC/MOF Requestor | Create CR/SOW | Customer Testing | Meeting To Be Scheduled | Pending Release | Grand Total
CAC | 3 | 2 | 1 | 2 | 8
FFX | 0 | 1 | 0 | 0 | 1
MOF | 5 | 1 | 0 | 0 | 6
Grand Total | 8 | 4 | 1 | 2 | 15
Status | Severity 2 | Severity 3 | Severity 4 | Grand Total
open | 1 | 0 | 0 | 1
resolved | 2 | 2 | 1 | 5
stalled | 4 | 2 | 2 | 8
started | 0 | 1 | 0 | 1
Grand Total | 7 | 5 | 3 | 15
Row Labels | Create CR/SOW | Customer Testing | Meeting To Be Scheduled | Pending Release | Grand Total
open | 0 | 1 | 0 | 0 | 1
resolved | 0 | 3 | 0 | 2 | 5
stalled | 8 | 0 | 0 | 0 | 8
started | 0 | 0 | 1 | 0 | 1
Grand Total | 8 | 4 | 1 | 2 | 15
CAC/MOF/FFX Owner | Severity 2 | Severity 3 | Severity 4 | Grand Total
CAC | 2 | 1 | 1 | 4
FFX | 3 | 2 | 1 | 6
MOF | 2 | 2 | 1 | 5
Grand Total | 7 | 5 | 3 | 15
Severity by Requestor | CAC | FFX | MOF | Grand Total
Severity 2 | 3 | 1 | 3 | 7
Severity 3 | 3 | 0 | 2 | 5
Severity 4 | 2 | 0 | 1 | 3
Grand Total | 8 | 1 | 6 | 15
Ticket Owner | Number of Tickets
FFX | 6
Ministry | 9
Grand Total | 15
Ticket Owner | # Sev 2 Tickets
CAC | 2
FFX | 3
MOF | 2
Grand Total | 7
Ticket Owner | Total # Tickets
CAC | 4
FFX | 6
MOF | 5
Grand Total | 15