## Sheet1
# | Customer | Subject | Status | QueueName | OwnerName | Priority | Defect # | Requestors | Created | Told | LastUpdated | Due | CustomField.{Current Status} | CustomField.{Ticket Severity}
104174 |  | SEV 3 - Batches in Error with No Message | resolved | Projects - Ontario - PROD | ben.whyte (Ben Whyte) | 10 |  | ben.whyte (Ben Whyte) | Mon, Apr 22, 2024 10:45:00 AM | Fri, May 24, 2024 2:44:44 PM | Tue, May 28, 2024 7:53:14 PM | Not set | Customer Testing | Severity 3
104204 |  | Payment Source Report Updates | ffxqa | Projects - Ontario - PROD | francesco.leising (Francesco Leising) | 10 |  | donna.schmitz (Donna Schmitz) | Tue, Apr 23, 2024 1:16:22 PM | Not set | Tue, May 28, 2024 9:58:35 AM | Not set | FFX Testing | Severity 2
104342 |  | CR75 - Daily Bank Deposit Summary Report | stalled | Projects - Ontario - PROD | jeff.jostes (Jeff Jostes) | 4 |  | brenda.boyle (Brenda Boyle) | Tue, Apr 30, 2024 10:06:48 AM | Not set | Thu, May 23, 2024 9:47:51 AM | Not set | Create CR/SOW | Severity 2
104379 | Cheque Negotiability Validation Rules - Updates Needed | Update Validation Rules - Cheque Negotiability | stalled | Projects - Ontario - PROD | tamara.gardner (Tamara Gardner) | 0 |  | tamara.gardner (Tamara Gardner) | Wed, May 1, 2024 9:42:41 AM | Not set | Thu, May 16, 2024 10:48:23 AM | Not set | Create CR/SOW | Severity 2
104385 |  | SEV 2 - Quick Print Transactions writing invalid $0.00 payments on F030 | resolved | Projects - Ontario - PROD | ben.whyte (Ben Whyte) | 8 |  | ben.whyte (Ben Whyte) | Wed, May 1, 2024 12:13:55 PM | Wed, May 29, 2024 2:16:22 PM | Wed, May 29, 2024 2:16:22 PM | Not set | Customer Testing | Severity 2
104412 |  | Sev 2: F060 MCR Credit Total & Debit Total Amounts are Incorrect | resolved | Projects - Ontario - PROD | aravinth.ramalingam (Aravinth Ramalingam) | 10 |  | aravinth.ramalingam (Aravinth Ramalingam) | Thu, May 2, 2024 12:23:54 PM | Wed, May 29, 2024 2:20:55 PM | Wed, May 29, 2024 2:20:55 PM | Not set | Customer Testing | Severity 2
104425 |  | SEV 3 - OPEX scanners accepting double feed without alerts | started | Projects - Ontario - PROD | jeff.jostes (Jeff Jostes) | 0 |  | ben.whyte (Ben Whyte) | Thu, May 2, 2024 4:15:21 PM | Not set | Thu, May 9, 2024 2:02:41 PM | Not set | Meeting To Be Scheduled | Severity 3
104470 |  | IMAGE Only - correspondence | resolved | Projects - Ontario - PROD | brenda.boyle (Brenda Boyle) | 9 |  | brenda.boyle (Brenda Boyle) | Tue, May 7, 2024 10:13:27 AM | Wed, May 29, 2024 10:54:31 AM | Wed, May 29, 2024 10:54:31 AM | Not set | Customer Testing | Severity 2
104480 | '20240507032682002 | SEV 3 - Operators prompted to key PostMark Date in ChequeOnly queue | resolved | Projects - Ontario - PROD | bukola.ogeleka (Bukola Ogeleka) | 10 |  | bukola.ogeleka (Bukola Ogeleka) | Tue, May 7, 2024 1:24:06 PM | Thu, May 16, 2024 1:00:32 PM | Wed, May 29, 2024 3:45:24 PM | Not set | Customer Testing | Severity 3
104523 |  | SEV 2 - Prevent $0.00 payment vouchers from advancing through Balance Queue | stalled | Projects - Ontario - PROD | ben.whyte (Ben Whyte) | 0 |  | ben.whyte (Ben Whyte) | Thu, May 9, 2024 10:54:17 AM | Not set | Thu, May 16, 2024 10:48:23 AM | Not set | Create CR/SOW | Severity 2
104539 |  | SEV 3 - MIT Virtual Voucher Validation Rule Change on Account ID | stalled | Projects - Ontario - PROD | jeff.jostes (Jeff Jostes) | 0 |  | ben.whyte (Ben Whyte) | Thu, May 9, 2024 3:05:42 PM | Mon, May 13, 2024 9:12:54 AM | Thu, May 16, 2024 10:48:23 AM | Not set | Create CR/SOW | Severity 3
104642 |  | New Report - Field Recognition Accuracy Detail Report by Batch Type | stalled | Projects - Ontario - PROD | jeff.jostes (Jeff Jostes) | 0 |  | tamara.gardner (Tamara Gardner) | Tue, May 14, 2024 11:31:52 AM | Not set | Thu, May 16, 2024 10:48:23 AM | Not set | Create CR/SOW | Severity 2
104684 |  | EditMoney Error - Correspondence_Rear with Separators | resolved | Projects - Ontario - PROD | brenda.boyle (Brenda Boyle) | 9 |  | brenda.boyle (Brenda Boyle) | Thu, May 16, 2024 8:10:15 AM | Not set | Tue, May 28, 2024 7:55:28 PM | Not set | Customer Testing | Severity 3
104806 |  | Sev 3: IFT_QUAR_RETU_L Invalid Data in Units Field, other Invalid Data OCR'd to output | resolved | Projects - Ontario - PROD | mariaalejandra.gonzalezmoctezuma (Maria Alejandra Gonzalez Moctezuma) | 10 |  | mariaalejandra.gonzalezmoctezuma (Maria Alejandra Gonzalez Moctezuma) | Tue, May 21, 2024 5:16:50 PM | Wed, May 22, 2024 8:20:09 AM | Tue, May 28, 2024 7:58:40 PM | Not set | Customer Testing | Severity 3
104830 | 20240522017169 | SEV 4: IFT Quarterly Return Allowing Negative Amount to be Entered in 'Interjurisdictional Units' field | resolved | Projects - Ontario - PROD | catherine.ryan (Catherine Ryan) | 10 |  | catherine.ryan (Catherine Ryan) | Wed, May 22, 2024 3:29:53 PM | Not set | Wed, May 29, 2024 3:19:01 PM | Not set | Customer Testing | Severity 4
104836 | 20240521940001000 | Sev 4 - Emails being split into multiple documents in EPIC | stalled | Projects - Ontario - PROD | lisa.parsons (Lisa Parsons) | 0 |  | lisa.parsons (Lisa Parsons) | Thu, May 23, 2024 9:25:52 AM | Not set | Thu, May 23, 2024 2:04:26 PM | Not set | Create CR/SOW | Severity 4
104843 |  | MIT Virtual Voucher- Installment payment type | stalled | Projects - Ontario - PROD | tamara.gardner (Tamara Gardner) | 0 |  | brenda.boyle (Brenda Boyle) | Thu, May 23, 2024 1:29:09 PM | Thu, May 23, 2024 2:39:21 PM | Thu, May 23, 2024 2:39:21 PM | Not set | Create CR/SOW | Severity 3
104851 |  | SEV 3 - Operators prompted to key incorrect documents in CreateLetter queue | resolved | Projects - Ontario - PROD | ben.whyte (Ben Whyte) | 10 |  | ben.whyte (Ben Whyte) | Fri, May 24, 2024 8:28:41 AM | Not set | Wed, May 29, 2024 4:26:31 PM | Not set | Customer Testing | Severity 3
104852 |  | Illegible DLN Burn on FTP supporting documents | stalled | Projects - Ontario - PROD | brenda.boyle (Brenda Boyle) | 0 |  | brenda.boyle (Brenda Boyle) | Fri, May 24, 2024 8:44:30 AM | Not set | Wed, May 29, 2024 5:53:51 AM | Not set | Create CR/SOW | Severity 4
104899 |  | SEV 2 - Transactions with multiple Post-Date Cheques sent back to start of Boundary 2, not going through CustomSplit | resolved | Projects - Ontario - PROD | ben.whyte (Ben Whyte) | 0 |  | ben.whyte (Ben Whyte) | Tue, May 28, 2024 10:40:16 AM | Tue, May 28, 2024 11:48:28 AM | Tue, May 28, 2024 7:55:02 PM | Not set | Customer Testing | Severity 2